Yanchep SLSC – Cost Estimate as at May 2014 (CoW) – refer IN03-05/14

| Item | Revised Expenditure Estimate | Budget |
| --- | --- | --- |
| Project Budget |  |  |
| Project PR-1048 Funding 2010/2011, with unexpended funding carried forward to 2011/2012 |  | $340,000 |
| Project PR-1048 Funding 2012/2013 |  | $200,000 |
| Project PR-1048 Funding 2013/2014 |  | $200,000 |
| Project PR-1048 Funding 2014/2015 |  | $6,400,000 |
| Overall Project Development & Implementation |  |  |
| Project Management (Internal) | $150,000 |  |
| Concept Development Consultation Fees including allowance for Geotechnical Investigation. | $90,000 |  |
| Power Supply (Consultant's Preliminary Cost Estimate) | $423,000 |  |
| Water & Sewer (Consultant's Preliminary Cost Estimate) | $240,000 |  |
| Stormwater Drainage to comply with WAPC requirement for 1:100 year storm event (Consultant's Preliminary Cost Estimate). | $180,000 |  |
| Retaining Wall Component linked to Stage 2 Brazier Road realignment works | $302,500 |  |
| Additional requirements for Coastal Assessment Study to comply with current gazetted State Planning Policy 2.6 | $10,200 |  |
| Coastal Hazard Risk Management and Adaption Plan. | $46,000 |  |
| Development and Detail Design Fees (estimate) | $300,000 |  |
| Tender Advertising and Signage | $7,000 |  |
| Construction of YSLSC and Public Amenities Facility | $4,027,000 |  |
| Car Park Construction | $845,000 |  |
| Total Order of Cost Estimates | $6,620,700 |  |
| Contingency Sum @ 10% on order of cost estimate | $662,070 |  |
| Total Funding | $7,282,770 | $7,140,000 |
| Additional Coastal protection works per CHRMAP Requirements (Refer IN02-08/14) | $450,000 |  |
| TOTAL COST ESTIMATE | $7,732,770 |  |